## Vendor Invoices
Corrective Action Plan
Processing of Vendor Invoices
Issue: Projects may not post all vendor invoices into the Project Management System, thereby distorting cost performance information and making the monthly review process somewhat non-value added.
Objective: Need to implement specific control procedures that will improve the current process ensuring that vendor invoices get posted in PMS.
[5 empty] | Run Test | Policy | Guide Book / | Std Operating | Impl | Est C | Measure | Final
Ref No | Describe Action Item | Scope of Action Item | Champion | Core Team / POC | Pilot? | Paper? | Training? | Procedure? | Date | Date | of Success | Resolution
Immediate Action Items
VS.1 | Develop and Distribute monthly General Ledger Reports on a project by project basis to all Project Managers so that they can review / reconcile vendor invoices | System Request required covering all IT projects setup in the General Ledger | PMO Director - Marshall Burley | Six Sigma Team and FRS Programmer | Yes - run several test of program before putting into production | No - this is below the policy level | Yes - develop training slides and conduct live meeting | Yes - reference this new activity in EVM Procedure 9 | TBD - Depends upon System Request | TBD - 30 days after System Request is 100% complete | All projects are using the new report to validate vendor invoices in PMS. | TBD - 3 months after implementation date
VS.2 | Payable processing is revised to include formal distribution of invoice copies to all IT Project Planners | Financial Accounting Control and IT Project Managers | PMO Director - Marshall Burley | Six Sigma Team and PMO | Not applicable | No | No | No |  |  | All projects are receiving copies of vendor invoices
VS.3 | All projects have a Project Planner assigned and trained in the posting of vendor invoices to the Project Management System | All IT Projects that should be using PMS | PMO Director - Marshall Burley | Six Sigma Team and PMO | Not applicable | No | Yes - update PMS Training Modules | Yes - update PMS SOP 11 |  |  | All projects have a trained planner assigned
Long Term Solutions
VL.1 | Develop an automated interface comparison on an invoice by invoice number basis between the General Ledger and the Project Management System. | All IT Projects setup in the General Ledger System | PMO Director - Marshall Burley | Six Sigma Team and PMO | Yes - run several test | No | Yes - will need to revise training | Yes - will need to update EVM SOP | TBD | TBD | All projects are using the web based tool
Glossary of Terms
EVM | Earned Value Management
FRS | Financial Reporting System
IT | Information Technology
PMO | Program Management Office
PMS | Project Management System
POC | Point of Contact
TBD | To Be Determined
www.chools.in
Note on A6: All action items must be assigned a reference number for tracking. Select V for Vendor Invoices or T for Timesheets followed by S for Short Term or L for Long Term and a number.
Note on B6: What specific procedure or change must get implemented?
Note on C6: Who must implement this change - what is the overall scope of this change?
Note on D6: Who is the sponsor / approver of this action item?
Note on E6: Who is the primary Point of Contact for this Action Item. Is a team assigned to implement this change?
Note on F6: Will this action item get implemented on a small scale at first, such as running a test pilot before full-scale implementation?
Note on G6: High Level Documentation: Does this change require a revision or new policy paper?
Note on H6: Mid Range Level Documentation: Does this change require some overall guidance and / or training for implementation?
Note on I6: Low Level Documentation: Will this change require very well defined and documented procedures in the form of an SOP - Standard Operating Procedure?
Note on J6: What is the anticipated date this change will get implemented?
Note on K6: What is the anticipated completion date for this change?
Note on L6: Describe a measure of success to monitor the implementation of this change?
Note on M6: Post Implementation: What is the final result of this change?

## Timesheets
Corrective Action Plan as of 12/10/07
Processing of Timesheets
Issue: Employees may not submit timesheets into the Project Management System, thereby distorting cost performance information and making the monthly review process somewhat non-value added.
Objective: Need to implement specific control procedures that will improve the current process ensuring that employees enter timesheets in PMS with each pay cycle.
[5 empty] | Run Test | Policy | Guide Book / | Std Operating | Impl | Est C | Measure | Final
Ref No | Describe Action Item | Scope of Action Item | Champion | Core Team / POC | Pilot? | Paper? | Training? | Procedure? | Date | Date | of Success | Resolution
Immediate Action Items
TS.1 | All Project Managers approve timesheets for all personnel assigned to the project | All IT Projects that use PMS | PMO Director - Marshall Burley & Chief Information Officer | Six Sigma Team and Project Managers | No | No | No | Yes - update SOP's | 2008-05-01 | 2008-06-01 | All Project Managers are approving timesheets
TS.2 | All employees assigned to a project must complete mandatory timesheet training with two weeks of being assigned to a project | All non-contract labor personnel assigned to an IT project | PMO Director - Marshall Burley & Chief Information Officer | Six Sigma Team and Project Managers | No | No | Yes - need to revise training and Guide | No | 2008-04-01 | 2008-05-01 | All assigned employees are entering timesheets
Long Term Solutions
TL.1 | Develop an automated email notification message each time an employee fails to enter their timesheet within a 24 hour period from the last date within each two week pay cycle. | All non-contract personnel assigned to IT projects | PMO Director - Marshall Burley | Six Sigma Team and PMS System Administrators | Yes | No | No | Yes - update SOP's once implemented | TBD | TBD | All assigned employees are entering timesheets
Note on A6: All action items must be assigned a reference number for tracking. Select V for Vendor Invoices or T for Timesheets followed by S for Short Term or L for Long Term and a number.
Note on B6: What specific procedure or change must get implemented?
Note on C6: Who must implement this change - what is the overall scope of this change?
Note on D6: Who is the sponsor / approver of this action item?
Note on E6: Who is the primary Point of Contact for this Action Item. Is a team assigned to implement this change?
Note on F6: Will this action item get implemented on a small scale at first, such as running a test pilot before full-scale implementation?
Note on G6: High Level Documentation: Does this change require a revision or new policy paper?
Note on H6: Mid Range Level Documentation: Does this change require some overall guidance and / or training for implementation?
Note on I6: Low Level Documentation: Will this change require very well defined and documented procedures in the form of an SOP - Standard Operating Procedure?
Note on J6: What is the anticipated date this change will get implemented?
Note on K6: What is the anticipated completion date for this change?
Note on L6: Describe a measure of success to monitor the implementation of this change?
Note on M6: Post Implementation: What is the final result of this change?