Revised 6-4-07

| Action Plan- Continuous Improvement (Dave’s Goal #2) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| List Goal: The Superintendent will present an action plan to the Board of Education that will provide detail of the plan to support continuous improvement efforts in the Cedar Rapids Community School District. The action plan will include components such as: A description of the research-based strategies and actions, in-process measures, targets, expected results, persons impacted, resources required and timelines for completion. |  |  |  |  |  |
| Goal Champion: Dave Markward, Jay Marino |  |  |  |  |  |
| Description of Proposed Action/Activity (What is going to be done to address this goal?) | Research/Rationale For Activity (Explain how best practices and research justify this activity) | Results (What will be the evidence of the impact on the goal) | Person(s) Impacted (Who will be involved?) | # Resources (Funding Source & Cost) | ## Timeline (When will the activity occur?) |
| a) Apply for Iowa Recognition for Performance Excellence (IRPE) Tier 2 application - Utilize feedback from the IRPE report to drive district strategic planning - Identify a champion for each opportunity for improvement b) Assess current levels of readiness for Performance Excellence criteria - Conduct a Baldrige Gallery Walk with the superintendent’s cabinet - Assess Executive Council’s level of buy-in for continuous improvement - Assess staff buy-in for continuous improvement c) Create a District Balanced Scorecard to gauge progress of the District strategic plan. - Identify appropriate measures tied to the 5 district strategic goals | The IRPE process closely mirrors the Malcolm Baldrige Criteria for Performance Excellence. The IRPE process will be used to gain feedback on our improvement efforts It is critical to determine the readiness of stakeholders as the continuous improvement journey progresses. Feedback from stakeholders will be used to drive future decision making. Effective organizations determine measures that will be used to gauge progress toward the strategic plan. | A completed Tier 2 application will be submitted to the IRPE Completed gallery walk with the critical few OFIs identified Completed evaluation/feedback from stakeholders to determine level of buy-in A completed Balanced Score Card posted online | Superintendent and Cabinet Accountability Office Superintendent and Cabinet | $500 Board Budget $500 Baldrige Budget No Cost | a) 7-30-2005 b) 9-2-2005 c) 12-2005 |

| Action Plan- Continuous Improvement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description of Proposed Action/Activity (What is going to be done to address this goal?) | Research/Rationale For Activity (Explain how best practices and research justify this activity) | Results (What will be the evidence of the impact on the goal) | Person(s) Impacted (Who will be involved?) | # Resources (Funding Source & Cost) | ## Timeline (When will the activity occur?) |
| d) Create outcomes for continuous improvement for each stakeholder group including: Cabinet/District, Schools/Departments, Teachers and students. Outcomes will be measurable and specific to the stakeholder group and will contain 4 quality levels. The outcomes will set and communicate direction and expectations for accomplishment over the next 3-5 years as stakeholders work through each of the 4 quality levels. e) Communicate and deploy the 4 quality levels to all stakeholder groups. Ensure that all stakeholder groups understand the expectation, direction and the resources available to accomplish the 4 quality levels. f) Plan and implement workshops, training and professional development opportunities for staff to learn more about continuous improvement and the 4 quality levels. Training efforts will be concentrated in the following areas: - Action Research Deployment Team workshops for all schools and support services departments - Online and interactive web site that contains files, presentations, templates, videos and other resources to support the accomplishment of the continuous improvement outcomes and quality levels - Workshops, seminars and training opportunities for individuals, building leadership teams or entire staff will be available. | Effective organizations set and communicate direction. Quality levels will establish expectations for all stakeholder groups in the area of continuous improvement. Direction must be shared and communicated to all stakeholders. Appropriate resources and support must be made available to stakeholders to effectively and realistically accomplish the specified outcomes. | The completion of the CRCSD 4 Quality Levels document for each stakeholder group A flow chart describing the communication of the 4 quality levels will be shared with administrators. A document will be created that outlines the various opportunities for training and support including times, dates and methods of participation | Accountability Office to draft quality levels and Executive Council to revise and provide input to final draft Accountability Office and Executive Council Accountability Office and Executive Council | $2000 State Farm Baldrige Grant $2000 State Farm Baldrige Grant $21,000 State Farm Baldrige Grant | d) 02- 2006 e) 04- 2006 f) 05- 2006 |

Action Plan- Continuous Improvement

| Description of Proposed Action/Activity (What is going to be done to address this goal?) | Research/Rationale For Activity (Explain how best practices and research justify this activity) | Results (What will be the evidence of the impact on the goal) | Person(s) Impacted (Who will be involved?) | # Resources (Funding Source & Cost) | ## Timeline (When will the activity occur?) |
| --- | --- | --- | --- | --- | --- |
| g) Create systems to provide internal support and build capacity to sustain continuous improvement efforts. The following initiatives will be conducted: - Create a Quality Liaison network for all schools and support services departments. Use this network to distribute expertise directly to the school and/or department. This group will learn how to support their school and department in the accomplishment of the 4 quality levels and how to effectively use continuous improvement processes and tools. - Increase the number of continuous improvement trainers in the CRCSD. Several teachers and administrators will be selected and trained as “Continuous Improvement Trainers.” These individuals will be certified to train other schools in the use of action research/PDSA and quality tools. They will also conduct workshops and training to directly support the accomplishment of the 4 quality levels. h) Create and deploy a “measurement instrument” that can gauge the level of deployment of the CRCSD 4 quality levels. This instrument will be standardized, communicated and results collected to determine level of implementation - A balanced score card measure will be identified (3D) “Increase % of staff implementing practices of the 4 Quality Levels.” - A self-assessment instrument will be created and implemented to help employees determine their own level of deployment of the 4 quality levels i) Prepare Iowa Recognition for Performance Excellence (IRPE) Tier 3 application - Utilize feedback from the IRPE report to drive district strategic planning - Identify a champion for each opportunity for improvement | Once initial training has occurred, it is critical that support processes be put into place to sustain efforts. A “decentralization” of expertise will occur to put the experts directly at the schools and departments. This ensures continuation of the continuous improvement initiative regardless of changes in leadership. What gets measured gets done. Effective organizations monitor and measure what is really important. Implementation data will be used to determine progress made and will allow for in-process adjustments to be made to the action plan. The IRPE process will be used to gain feedback on our improvement efforts. | The creation of the Quality Liaison network with scheduled meetings and agendas. The scheduling of “train the trainers” workshops A final deployment measurement instrument that is communicated and shared with all District staff Create a balanced score card measure (3D) The communication of the Deployment Instrument to staff A completed Tier 3 application will be submitted to the IRPE | Accountability Office and Executive Council Accountability Office and Executive Council Superintendent and Cabinet | District Baldrige Fund *$40,000 for Quality Liasn. *25,000 for train the trainer District Baldrige Fund $1,500 $5000 Board Budget | g) Monthly Quality Liaison Meetings 07- 2006 Train the Trainer Wkshp h) 08- 2006 i) 7-30-2006 |

Action Plan- Continuous Improvement

| Description of Proposed Action/Activity (What is going to be done to address this goal?) | Research/Rationale For Activity (Explain how best practices and research justify this activity) | Results (What will be the evidence of the impact on the goal) | Person(s) Impacted (Who will be involved?) | # Resources (Funding Source & Cost) | ## Timeline (When will the activity occur?) |
| --- | --- | --- | --- | --- | --- |
| k) Evaluate stakeholder “buy-in” to the District strategic direction. - Evaluate the September 1st, staff learning day activities (Certified staff and administrators feedback) - Evaluate the September 1st, staff learning day activities Support Staff feedback - Share evaluation feedback with stakeholders, administrators and the board of education. l) Continue District-wide Action Research Deployment Team workshops for certified staff and administrators. Focus on deeper understanding and implementation of the Plan, Do, Study, Act cycle of continuous improvement. - Evaluate each workshop to determine effectiveness m) Revise format for Support Services Departments workshops. Create a new model of continuous improvement that specifically meets the needs of support services departments. - Meet with support service department supervisors and conduct a “current state vs. desired state” discussion. Use input to draft a model for support services. - Create a model for support services departments and seek input from cabinet. - Schedule 4 meetings and conduct workshops for support services departments n) Continue Quality Liaison network. Expand membership to include all schools. - Schedule monthly meetings | As the District sets and communicates direction, it is critical to determine stakeholder perception of the change process. In order to carry out the Guiding Philosophy of Continuous Improvement, school teams need to become proficient in the PDSA cycle District support service departments need access to continuous improvement processes and tools that are different than what the schools receive. A plan will be customized to the needs of support services to align with district continuous improvement efforts To sustain our continuous improvement efforts, a network of “specialists” will be maintained. | Report to the board of education sharing a summary of the evaluation of the September 1st, 2006 Staff learning day A schedule of 4 workshops during the year. Utilization of the PDSA cycle for SIP goals A plan for support service departments to learn more about continuous improvement A Quality Liaison meeting schedule to include monthly meetings | Accountability Office All school’s Building Leadership Teams Support Services Departments All schools | $0 $45,000 District Baldrige Fund $10,000 District Baldrige Fund $50,000 District Baldrige Fund | September 25th, 2006 Quarterly during 06-07 year Quarterly during 06-07 year Monthly meetings during the 06-07 year |

Action Plan- Continuous Improvement

| Description of Proposed Action/Activity (What is going to be done to address this goal?) | Research/Rationale For Activity (Explain how best practices and research justify this activity) | Results (What will be the evidence of the impact on the goal) | Person(s) Impacted (Who will be involved?) | # Resources (Funding Source & Cost) | ## Timeline (When will the activity occur?) |
| --- | --- | --- | --- | --- | --- |
| o) Meet monthly with principals to continue developing their skills and knowledge of continuous improvement processes and tools. - Seek monthly input from administrators - Provide activities to deepen knowledge of quality tools, Action Research and the 4 Quality Levels p.) Roll-out the Continuous Improvement Classroom Deployment Instrument to all schools - Obtain baseline data from all schools to form a “district average score” - Ensure 4 Quality Levels are being implemented - Develop 4 Quality Levels for specific groups (PE, Music, Media, etc.) q.) Develop stakeholder surveys for the following stakeholder groups (see Stakeholder Satisfaction Survey Action Plan for detail): - Students - Staff - Parents r.) Continue to work on OFIs from the 2006 IRPE feedback report. - Utilize feedback from the IRPE report to drive district strategic planning - Identify a champion for each opportunity for improvement from the feedback report | Principals have requested more information about continuous improvement. School leaders need to be competent in their skill and ability to lead the school’s continuous improvement efforts Measurement of progress is essential. Progress will be measured by assessing deployment of the 4 Quality Levels. It is critical that all educators understand their role in continuous improvement In order to determine progress made on our core value of customer satisfaction, instruments need to be created to measure satisfaction levels. The IRPE score gives us a measure of progress in our continuous improvement journey. Feedback reports help drive improvements as well. | A portion of each agenda will be devoted to addressing continuous improvement issues Obtain baseline measurements of 4 Quality Level deployment The creation of survey instruments for all stakeholder groups Submission of a Tier 2 IRPE application | School administrators All schools, Quality Liaisons All staff, parents, students and community members Superintendent’s cabinet | $0 $100 District Baldrige Fund $55,000 District Baldrige Fund $5000 Board Budget (includes feedback report and site visit) | Monthly meetings during the 06-07 year April, 2007 April, 2007 June, 2007 |