## Roadmap
ACME Continuous Improvement Roadmap
| Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
Governance | Consultancy Support Agreed | CI Steering Team | Success metrics |  | Road Map Published |  | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review | Road Map & Metric Review
| CI Champion | VSM and Project Selection |  |  | Project Tracking Document | Project review | Project review | Project review | Project review | Project review | Project review | Project review | Project review | Project review | Project review
| Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
[12 empty] | Author: | B Rushe | www.chools.in
Note on B2: Rolling 12 - 18 month window. Update monthly or quarterly
Note on B5: Managemnt structure & processes for the CI programme i.e. steering team, champion selection, and project selection and review process. The steering team (probably the management team) reviews the overall roadmap monthsly. The Champion reviews all projects monthly.
Note on B8: All projects recorded here e.g. BB, GB and YB, and capital projects
Note on B15: One area at a time. Approx 3 -4 months in each area until 5S embedded
Note on B19: Continuous ongoing activity based learning to support the CI programme and projects

## Project master list
Project Area | Project Number | Project Title | Team Lead | Sponsor | Pending Active Complete | Red Amber Green | Comment | Key
Green Belt | A |  |  |  | Active |  |  |  | OK
Green Belt | B |  |  |  | Active |  |  |  | In danger
Green Belt | C |  |  |  | Active |  |  |  | Behind schedule
Green Belt | D |  |  |  | Pending |  |  |  | Pending
Yellow Belt | E |  |  |  | Active
Yellow Belt | F |  |  |  | Pending
Yellow Belt | G |  |  |  | Pending
Capital | H |  |  |  | Pending
Yellow Belt | I |  |  |  | Pending
5S | 1 |  |  |  | Active
5S | 2 |  |  |  | Pending
5S | 3 |  |  |  | Pending
5S | 4 |  |  |  | Pending
5S | 5 |  |  |  | Pending
Project Review group: |  | John Greggs (CI Champion), Mary McEnroe (eng mgr), Marty Fields (HR mgr) |  |  |  |  | www.chools.in
Review frequency: |  | Monthly
Time: |  | 08.30am, first Thursday of every month
Venue: |  | Room 123

## Project tracker
MASTER PROJECT TRACKER
Project 14-001 | Energy reduction in building B
Team Lead | Tom Sullivan, ext 1234 | [8 empty] | Project Sponsor |  |  |  |  | Mary McEnroe, ext 5678
Project Stage | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Key
Define | [41 empty] | Planned | bar: Tom Sullivan, ext 1234 Wk 1 to Tom Sullivan, ext 1234 Wk 3
Measure | [41 empty] | Complete | bar: Tom Sullivan, ext 1234 Wk 3 to Tom Sullivan, ext 1234 Wk 5
Analyse | [41 empty] | In danger | bar: Tom Sullivan, ext 1234 Wk 5 to Tom Sullivan, ext 1234 Wk 7
Improve | [41 empty] | Behind schedule | bar: Tom Sullivan, ext 1234 Wk 7 to Project Sponsor Wk 14
Control | bar: Project Sponsor Wk 14 to Mary McEnroe, ext 5678 Wk 23
Project B | bar: Tom Sullivan, ext 1234 Wk 1 to Mary McEnroe, ext 5678 Wk 21
Team Lead | Project Sponsor Wk 10: Project Sponsor
Project Stage | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40
Define
Measure
Analyse
Improve
Control
Project C | bar: Wk 1 to Project Sponsor Wk 21
Team Lead | Project Sponsor Wk 10: Project Sponsor
Project Stage | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40
Define
Measure
Analyse
Improve
Control
www.chools.in
Note on A2: Unique project number
Note on A10: Unique project number
Note on A18: Unique project number
Note on B2: Project title
Note on B3: Team lead name
Note on B10: Project title
Note on B11: Team lead name
Note on B18: Project title
Note on B19: Team lead name
Note on P3: Sponsor name
Note on P11: Sponsor name
Note on P19: Sponsor name