## Stakeholder Analysis
Stakeholder Analysis
Cost Data Integrity Project
Stakeholder | Stakeholder Interest | Influence / Power | Level of Interest | Where do we need them | Strategy / Communication to Stakeholder
Chief Information Officer (CIO) | Wants to see a reliable and dependable process in place regarding cost performance of IT investments | 9 | 9 | Sponsor the project, make recommendations on implementing project solutions, and issuing communications directly to Project Managers | Bi Weekly updates provided by the PMO Director
Director of Project Management Office (DPMO) | Needs to provide the CIO and others with assurance that the process has been fixed and is working | 4 | 10 | Sponsor the project, approve the project schedule, direct communications to senior leadership, and provide personnel and general support to the project | Weekly status meetings with the PMO Director and his staff
CIO Goverance Council (CIO-GC) | Approves the final work products produced from the project and wants to see successful implementation of solutions | 8 | 7 | Review results of the project at each phase, approve project deliverables and work products, and sponsor / support the implementation of solutions | Monthly briefings on project results and work products
IT Directors and Managers (ITDM) | Need to see a consistent and reliable process for evaluating IT investments | 6 | 7 | Champion the solutions to their program areas and monitor the progress of implementation, report back the results to CIO Council and other senior leaders | Distribute monthly CIO Council Briefings to this group and invite to critical meetings as the project nears completion and begins implementing solutions
Project Managers (PM) | For those that want to see good performance data, there is solid interest. Other Project Managers consider proper accounting a wasted exercise outside the area of project management. | 5 | 4 | Leverage those Project Managers that agree the process is broken and highlight their success to drive full scale implementation to other projects that ignore project recommendations and solutions | Identify and include a group of Project Managers with test piloting proposed solutions. Include this same group in progress reports throughout the project life cycle. This would include communicate updates / news alerts to the entire population of Project Managers
Project Staff - Analyst, Schedulers, Planners, etc. (PM Staff) | Most of the project staff concur with the need to mature the current process and put better controls in place. | 3 | 4 | During full-scale implementation of solutions, most of the project staff will be impacted. May have to involve some project staff during Measurement and Analysis phase. | Include senior staff level people with all pilot testing and any final briefings or communications that are directed at educating people on changes to the existing processes.
Budgeting Department (BD) | Expect good reliable numbers from reports provided by the Project Managers. | 4 | 8 | Support the mission of this project and its solutions since this impacts the integrity of how they do their job and the reliability of what they distribute to others. | Copy them with communicate updates / news alerts that are going out the Project Managers.
External Agencies (EA) | Expect good reliable numbers from reports provided by the Agency | 6 | 2 | Once solutions are fully implemented and depending upon the extent of the problem, may need to notify or brief those agencies that have relied heavily on cost performance data in the past. | Have the CIO Brief those outside agencies that are heavily impacted by the changes implemented as a result of this project.
www.chools.in
Note on C4: On a scale between 1 (no power / influence) and 10 (extreme power / control), how much influence and power does this stakeholder have with the final goals and objectives of this project.
Note on D4: On a scale between 1 (no interest at all) and 10 (extremely interested), how much interest does this stakeholder have in the outcomes of this project?
Note on E4: Based on the ratings assigned for Power / Influence and Interest, what is the best way to leverage this stakeholder so that this project can meet its objectives and goals.
Note on F4: Based on the ratings for Power / Influence and Interest, describe how this project will communicate with this stakeholder.

## Graph
Stakeholder Analysis Graph
Cost Data Integrity Project
High
Low
| Low | High
Keep
Satisfied
Manage
Closely
Monitor
Casually
Keep
Informed
CIO
DPMO
Interest
Power
CIO-GC
ITDM
PM
PM-Staff
BD
EA