## Five Why - Timesheets
Five Why Analysis
Timesheet Processing
Cost Data Integrity Project
1st Why?
Why are employees not entering timesheets into the Project Management System?
↓
2nd Why?
Why are Project Managers not requiring a timesheet from personnel assigned to the project?
↓
3nd Why?
Why do Project Managers fail to recognize the cost impact of timesheets not processed?
↓
4nd Why?
Why do Project Managers fail to understand how project accounting works and its impact on project management?
↓
5th Why?
Why do we not require some form of training on project accounting and its connection to project performance reporting?
Corrective Action
Level of Five Why
Immediate Action Steps:
1. Expand current training and procedures to address timesheets and costs
www.chools.in

## Five Why - Invoices
Five Why Analysis
Vendor Invoices
Cost Data Integrity Project
1st Why?
Why are projects not capturing and entering vendor invoices?
↓
2nd Why?
Why are projects not receiving copies of vendor invoices?
↓
3nd Why?
Why are payable processing control points not distributing vendor invoices?
↓
4nd Why?
Why are control points for projects not aware of the invoice processing flows?
↓
5th Why?
Why is there not a direct comparison between payable records (General Ledger) vs. project accounting records?
Corrective Action
Level of Five Why
Immediate Action Steps:
1. Explore developing a reconciliation control procedure to close this gap
2. Document the control procedure with training
www.chools.in