## Estimating template guidelines
Delete this sheet before submitting estimate
Start with "the Costs number" provided in the Business Case during Phase 0 …
Project Costs as defined in the Business Case template instructions are:
…. any costs related to completing this project including: development costs,
software costs, hardware costs, etc. as well as ongoing support costs.
As a starting point, apportion the cost dollars across the Phases of the project. (Tops Down estimate)
Further breakdown the phases of the project into a task/activity list for each phase.
Estimate the effort & costs for the project against the task/activity list (see the "effort" tab)
(Consider the following areas in estimating your software development (or upgrade) project :)
Development Effort - (time*rate) by resource type, by project phase, by task/activity
Hardware Costs
Software Costs
Networks
On-going support Costs
Admin costs (above typical overhead)
For increased accuracy, re-estimate the project using a bottoms up approach and reconcile the major differences
between the Top down and the Bottoms up estimates.(Whenever possible seek an independent validation of the
estimate before providing it to your Client.)
Document the risks assessed and assumptions made that support the estimate.
The various tabs in this workbook are intended as aids in estimating I.S. projects.
Please note … the various sample tables, and estimating checklists, used throughout the workbook are intended as
guidelines or examples for potential tables to be used for individual projects. In many cases, experienced
Project Managers will have far more sophisticated tables that will better serve the project. These should
definitely be substituted for the table in the workbook. Where the Project Manager does not have such an instrument,
the workbook tables might serve as a base for what is needed for the project being estimated.
The colors and markings in this workbook have the following meanings.
Green Cells = Calculated Numbers
Gray Cells = numbers or fields to be supplied by template user.
Project: Encompassing the totality of the undertaking. | Other colors/patterns have no meaning other than formatting
See the estimating Workbook presentation for information on how to use the estimating tabs.
www.chools.in

## Pre-estimate checklist
Pre-estimate checklist:
Project Process | Yes | No | not necessary
Requirements
Are the Project Requirements clearly documented and Understood? |  | X
(by both I.S. and the Client?)
Is the criteria for meeting each requirement defined? |  | X
Are the Project Requirements Baselined (Under change control)? |  | X
Is there a "Client approved" plan for Requirements changes? |  | X
Has a Requirements Traceability Matrix been developed? |  | X
Have the requirements been validated against the business objectives? |  | X
Have you considered all of the processes that must be followed during |  | X
the project life cycle?
Have you considered all of the interfaces that must be adhered to? |  | X
Scoping
Has a Statement of Work (SOW) been reviewed/approved by the Client |  | X
Has the Statement of Work been reviewed by the virtual |  | X
team partners?
Has a Work Breakdown Structure (WBS) been reviewed by the Client |  | X
Has the WBS been reviewed by the virtual team partners? |  | X
Risk
Has a formal Risk Assessment been done? |  | X
(including probability, impacts, avoidance & recovery)
Is there an approved Risk Management Plan? |  | X
Was a Client representative involved with the Risk Management Plan? |  | X
Were appropriate I.S. resources involved in the Risk Management Plan? |  | X
Environments
Is the process for identifying, acquiring, establishing, and verifying the |  | X
environment understood and included in the plans for the project?
Is the Development environment adequate to support the project? |  | X
Is the Operational environment adequate to support the project? |  | X
Staff
Are appropriate staff available for the project? |  | X
Are the resources committed to participate in the required activities? |  | X
Is there a training plan to cover deficiencies? |  | X
www.chools.in

## Project Assumptions
Replace this sheet with a "Project Assumptions" sheet.
ALWAYS include a complete description of the assumptions and dependencies that
support the estimate.
Assumptions
Estimating usually involves making assumptions. It is important to record these
assumptions. As the project progresses, the estimating assumptions should be
reviewed and revised. To whatever degree possible, the project's scope definition
should be included in the assumptions.
Assumptions can be recorded using a format similar to the following:
| Assumption | A description of the assumption.
The part of the project to which this assumption applies. For
| Applicability | example, the assumption may apply to the whole project, or to just
a stage, such as Business Process Redesign.
| Status | Indicates whether the assumption is still valid.
| Resolution | Describes the resolution of any issues highlighted by the
assumption, if applicable.
The estimating assumptions can be combined with scheduling assumptions.
www.chools.in

## (1) Estimate summary
Department name |  |  | Project name/Number
Project Manager Name, PM |  |  | Date
| Effort | 0
| Hardware | 0
| Software | 0
| NetWorks | 0
| On-going support | 0
| Admin costs not in overhead | 0
| Sub Total | 0
| Risk | 0 |  | Project Risk Factor
| Change | 0 |  | Project Change Factor
| Total (includes Risk & Change) | 0
www.chools.in

## (2) Effort
Total "Effort estimate" |  |  | 0
Project Name/Number ______________ | [7 empty] | Project Manager __________
Date __________
Project Activity/Task ID (#) |  | Project Activity/Task name/description | Resource type | Resource Quantity (by type) * | rate per hour | Effort hours required | estimated effort cost (sub total) | Remarks
0
[6 empty] | Total | 0
|  | Resource type | estimated | not estimated * |  | Resource type estimate checklist:
IS Project Team
|  | Project Manager |  | X
|  | Project Leader |  | X
|  | Analyst |  | X
|  | Programmer |  | X
|  | Tester |  | X
|  | Documentation |  | X
|  | Third Party Prime (e.g. EPIC, Origin, BaaN) |  | X
|  | BaaN Core Program Interface Prime |  | X
|  | Integration Partners Core |  | X
|  | Integration Partner Non-Core |  | X
IS Support Functions
|  | New Product Introduction (NPI) Prime |  | X
|  | DBA |  | X
|  | Processing Services Prime |  | X
|  | Desktop Prime |  | X
|  | Networking Services Prime |  | X
|  | Vendor Management Prime |  | X
|  | Deployment Prime |  | X
|  | Captive Office Prime |  | X
|  | Functional Design Expert |  | X
|  | Detail Design Expert |  | X
IS Other
|  | Configuration Management Prime |  | X
|  | Client Manager |  | X
|  | Internal Audit |  | X
|  | Quality Assurance Prime |  | X
|  | Product Prime |  | X
|  | Program Office Prime |  | X
|  | Release Manager |  | X
Client
|  | Client Prime |  | X
|  | DEM Prime |  | X
|  | Process Prime |  | X
|  | Indirect |  |  |  | Indirect estimate checklist:
| Subject Matter Experts from Client Organizations |  |  | X
| Subject Matter Experts from other IS depts. |  |  | X
| Employee Advisory Committees |  |  | X
| Client Advisory Committee |  |  | X
| Vendor Management |  |  | X
Userid Administration
| Data Standards Forum |  |  | X
| Data Management |  |  | X
| Architecture |  |  | X
| Core Baan Program interface organization |  |  | X
| Integration Testing |  |  | X
| Item |  | estimated | not estimated * |  | Project support estimate checklist:
| Database Administration |  |  | X
| Resource Management |  |  | X
| Verification and Validation |  |  | X
| Configuration Management |  |  | X
| Quality Assurance/Facilitation |  |  | X
| Electronic Data Interchange |  |  | X
| New Product Introduction |  |  | X
| Product Management |  |  | X
| Core Baan Program Interfaces |  |  | X
| Networking and Computing |  |  | X
| Processing Services |  |  | X
| Finance |  |  | X
| Application Modifications - vendor |  |  | X
| Third Party Suppliers(e.g. EPIC, Baan, Origin) |  |  | X
| IS Skills Development |  |  | X
| 3rd party warranty support vs contracted support. |  |  | X
| computer operations support |  |  | X
| outsourced support |  |  | X
| Level-1/Level-2 support |  |  | X |  |  | www.chools.in

## (3) Hardware
Total "Hardware Cost estimate" |  |  |  |  | 0
Sample table
| Server Hardware … | Price per unit | Quantity | Total |  | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
| Desktop Hardware … | Price per unit | Quantity | Total |  | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
0
Hardware estimate checklist:
| Item |  | estimated | not estimated *
| Cpu Hardware |  |  | X
| Servers |  |  | X
| Modem |  |  | X
| Extraordinary power supply |  |  | X
needs
| Backup Systems |  |  | X
| Disaster Recovery Systems |  |  | X
| Additional Memory |  |  | X
| Processing Services |  |  | X
| Disk Storage |  |  | X
| Tape Backup |  |  | X
| UPS |  |  | X
| Switching devices |  |  | X
| Routers |  |  | X
| Racks |  |  | X
www.chools.in
| Local taxes |  |  | X
| shipping, handling(delivery) |  |  | X
| installation |  |  | X

## (4) Software
Total "Software Cost estimate" |  |  |  | 0
Sample table
| Server Software … | Price per unit | Quantity | Total | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
| Desktop Software … | Price per unit | Quantity | Total | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
0
Software estimate checklist:
| Item | estimated | not estimated *
| Application Licenses |  | X
| Security (Nortel.Access) |  | X
| RDBMS Licences |  | X
| Project specific Software tools |  | X
| Application Mods - vendor |  | X
| Any costs that this project must bear |  | X
to decommission Legacy Systems
| Archiving |  | X
| Communication SW (e.g. MQ Series) |  | X
| Userid Administration |  | X
| also include: |  | X
| The number of licenses |  | X
| Any installation costs |  | X
| S&H costs |  | X |  |  | www.chools.in
| support costs |  | X

## (5) Network HW-SW
Total "Network Cost estimate" |  |  |  | 0
| Server Network needs … | Price per unit | Quantity | Total |  | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
| Desktop Network needs … | Price per unit | Quantity | Total |  | Supporting information
| for development |  |  | 0
| for test |  |  | 0
| for training |  |  | 0
| for production |  |  | 0
| Total (Server) |  |  | 0
0
Network estimate checklist:
| Item |  |  |  | estimated | not estimated *
| LAN |  |  |  |  | X
| WAN |  |  |  |  | X
| Routers |  |  |  |  | X
| Dial-up Lines |  |  |  |  | X
| Dedicated lines |  |  |  |  | X
| Satellite |  |  |  |  | X
| Ports |  |  |  |  | X
| Phones |  |  |  |  | X
| Controllers |  |  |  |  | X
| Switches |  |  |  |  | X
| SW licenses |  |  |  |  | X
| Setting up Access (e.g. Secure ID) |  |  |  |  | X
| Other security … Firewall, etc. |  |  |  |  | X
Processing Services
| (estimate 15-20% of the hardware costs per annum) |  |  |  |  | X
www.chools.in

## (6) On-Going Support
Total "On-going support estimate" |  |  |  | 0
| On-Going support items |  |  | 0 | Supporting information
Disaster Recovery
Depreciation costs
0
"On-going" support estimate checklist:
| Item |  |  | estimated | not estimated *
Level-1/L-2 support (Level of service - Platinum, Gold, Silver, Bronze)
| New user setup |  |  |  | X
| Password/User ID restores |  |  |  | X
| Archiving of data |  |  |  | X
| Emergency Recovery |  |  |  | X
| Data integrity issues |  |  |  | X
| Regular Job scheduling |  |  |  | X
| Ad-hoc production job scheduling requests |  |  |  | X
| Report generation & Elimination |  |  |  | X
| Procedures Clarification |  |  |  | X
| Ticket Status Updates |  |  |  | X
| Scheduled maintenance |  |  |  | X
| Recovery from failed job |  |  |  | X
| Information flow monitoring |  |  |  | X
| Standard Backups (non-Mac or PC) |  |  |  | X
| System Availability Monitoring & Correction |  |  |  | X
| System Recovery |  |  |  | X
| Disk space management (non-Mac or PC) |  |  |  | X
| Basis Security Services and Precautions |  |  |  | X
| Root Cause Analysis |  |  |  | X
| Problem Resolution |  |  |  | X
| Liason with DBA, Networks, Local I/S |  |  |  | X
| Patch Maintenance |  |  |  | X
| Time Zone Coverage |  |  |  | X
| Multiple Site Support |  |  |  | X
| Client - Support Communication |  |  |  | X
| Site to Site Communication |  |  |  | X
Level - 3 Support (above items plus):
| Bug fixes |  |  |  | X
| Test Environment Costs |  |  |  | X
Pre-Implementation Support:
| Product Support during SIT/BIT/NIT Testing |  |  |  | X
Release Strategy Support:
| Bug and Enhancements |  |  |  | X
| Implementation |  |  |  | X
| Customization |  |  |  | X
"On-going" support estimate checklist: (cont'd)
| Item |  |  | estimated | not estimated *
GES Renderings:
| Job scheduling |  |  |  | X
| Scheduled maintenance |  |  |  | X
| Standard Backups (non-Mac or PC) |  |  |  | X
| System Availability Monitoring & Correction |  |  |  | X
| OS Patch Maintenance |  |  |  | X
DBA:
| Back-up |  |  |  | X
| Scheduled maintenance |  |  |  | X
| DB Availability Monitoring & Correction |  |  |  | X
| DB Patch Maintenance |  |  |  | X
Network management:
| Back-up |  |  |  | X
| Scheduled maintenance |  |  |  | X
| NW Availability Monitoring & Correction |  |  |  | X
| NW Patch Maintenance |  |  |  | X
Hardware, Storage (DASD), etc. (requirements for near & long-term)
Lease Penalties
Disaster Recovery
Depreciation costs
www.chools.in

## (7) Admin costs not in overhead
Total estimate for |  |  | 0
Admin costs not in overhead
Sample table
| Admin items |  |  | Supporting information
Travel
Facilities(real estate)
etc.
0
"Admin costs not in Overhead" estimate checklist:
| Item |  | estimated | not estimated *
| Conferences |  |  | X
| Internal or external |  |  | X
| Face to Face meetings |  |  | X
| Audio/Video teleconferences |  |  | X
| Internal Audit |  |  | X
Quality Assurance
| extraordinary Communications |  |  | X
| Printing (e.g. manuals, training material) |  |  | X
| Project Website development and maintenance |  |  | X
| Use of Learning Institute |  |  | X
| Administration support |  |  | X
| Marketing |  |  | X
| Electrical work |  |  | X
| network connections |  |  | X
| lighting |  |  | X
| furniture |  |  | X
| special Air conditioning |  |  | X
| Team recognition/celebration |  |  | X
www.chools.in

## Risk & Change
Replace this page with your project risk chart
The following is provided as a basic template that may be used in the
analysis and documentation of project risks:
|  | Probability of Occurrence |  |  | Impact |  |  | Planned Action
Risk number | Activity/Requirement | low | medium | high | low | medium | high | no action | type of action | Risk weight *
www.chools.in