## Example
2-Years Improvement Roadmap
| Business function: | Manufacturing | Leader: |  | Current year:
| Improvement period: |  | Start date: |  | End date:
| Rev. No.: |  | Rev. date.:
| Improvement Goal | Baseline performance Where we are now | Where we want to be in 6 months | Where we want to be in 12 months | Where we want to be in 18 months | Where we want to be in 24 months | Metric
1 | Spoilage reduction | Spoilage rate is too high (>8%) | Defect awareness program to all | Breakdown analysis system in place | Spoilage rate less than 5% | Spoilage rate less than 4% | Spoilage rate | Not started
|  |  | Completed | Completed |  |  |  | 25% or less
2 | Internal audit development | Internal audit is not effective enough (last audit score was 63.4%) | Current audit practices reviewed and improved | Audit system covers all functional areas | Audit score above 80% | Audit score above 90% | Audit score | 50% or less
|  |  | 99% or less | 75% or less |  |  |  | 75% or less
3 | 5S improvement | Poor workplace organization and conditions (5S audit score is 54%) | 5S awareness program to all | 5S procedures and practices in place | 5S audit score above 75% | 5S audit score above 85% | 5S audit score | 99% or less
|  |  | 75% or less | 25% or less |  |  |  | Completed
4
5
www.chools.in