## Project Selection
Improvement Projects - Selection |  |  |  |  | Year:
Methodology
| # | Project Title | Sponsor | Project Type | Saving Type | Approach | PPM Score | PPI Score | Comments
1 | 445 | Spoilage reduction (Line 4) |  | Cost reduction | Hard | Six Sigma | 4.76 | 20.9524 |  | Cost reduction
2 | 461 | Stretch film wrapping usage reduction |  | Cost reduction | Hard | Quick wins | 1.32 | 16.2273 |  | Revenue enhance
3 | 414 | Energy consumption reduction |  | Health and safety | Hard | Other | 1.69 | 3.9018 |  | Satisfaction
4 | 557 | Packaging material usage reduction |  | Cost reduction | Hard | Six Sigma | 2.98 | 3.8481 |  | Cash flow
5 | 213 | Coolant usage reduction |  | Cost reduction | Soft | Six Sigma | 2.06 | 2.5143 |  | Capital
6 | 432 | 5S implementation in workshop area |  | Satisfaction | Soft | Lean | 3.38 | 5.9429 |  | Cost avoidance
7 | 591 | Changeover time reduction (Line 4) |  | Revenue enhance | Hard | Lean | 2.86 | 14.0914 |  | Risk avoidance
8 | 474 | Paper and cartridge usage reduction |  | Health and safety | Soft | Kaizen | 0.97 | 4.7407 |  | Health and safety
9 | 493 | Waste reduction (Line 6) |  | Cost reduction | Hard | Six Sigma | 5.32 | 14.3544 |  | Regulatory compliance
10 | [9 empty] | Other
11
12 | [9 empty] | Hard
13 | [9 empty] | Soft
14
15 | [9 empty] | Six Sigma
Lean
Kaizen
Reengineering
| Conclusion / Comments: | [8 empty] | Traditional PM
Quick wins
Other
www.chools.in
Guidelines:
This worksheet uses two methods to help in the project selection process: the Project Prioritization Matrix (PPM) and the Pareto Priority Index (PPI).
1st: List the candidate improvement projects. 2nd: Identify the project type and the approach to be used. 3rd: Use any or both of the selection methods in your prioritizing and selection of projects.
You need only to fill the white cells.
Definitions:
Cost reduction - Results from savings in operating or capital costs
Revenue enhancement - Production capacity is increased to meet higher demands
Satisfaction - Higher satisfaction levels among main stakeholders
Cash flow - Re-examining the spending habits and the way cash flow works (e.g. late receivables or early payables)
Capital projects - Reduction in the need for working capital or eliminate future capital from the capital plan
Cost avoidance - Deferred or eliminated future expenses that have never occurred and there is no baseline spending (e.g. overtime)
Risk avoidance - More effective management of risks resulting from inadequate internal processes, people, systems, or external events
Environment, health or safety -
Regulatory compliance -
Hard savings - Contribute to the bottom line (mainly revenue enhancement or cost reduction)
Soft savings - More difficult to quantify and savings will occur in the future

## Method 1 - PPM
Improvement Projects - Selection - Project Prioritization Matrix
[11 empty] | Methodology |  | Index value
|  | # | Project Title | Sponsorship | Benefits to stakeholders | Team members | Resources availability | Learning opportunity | Time to complete | Deliverables | Technique used | Image of company | PPM
|  |  | Weight | 0.21 | 0.24 | 0.11 | 0.12 | 0.09 | 0.11 | 0.04 | 0.07 | 0.01 | 1
| 1 | 445 | Spoilage reduction (Line 4) | 1 | 9 | 3 | 3 | 9 | 1 | 3 | 9 | 3 | 4.76
| 2 | 461 | Stretch film wrapping usage reduction | 3 | 0 | 1 | 1 | 1 | 3 | 1 | 0 | 0 | 1.32
| 3 | 414 | Energy consumption reduction | 3 | 1 | 1 | 1 | 3 | 1 | 0 | 3 | 0 | 1.69
| 4 | 557 | Packaging material usage reduction | 1 | 3 | 3 | 1 | 9 | 1 | 1 | 9 | 1 | 2.98
| 5 | 213 | Coolant usage reduction | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 0 | 0 | 2.06
| 6 | 432 | 5S implementation in workshop area | 3 | 3 | 3 | 1 | 9 | 1 | 0 | 9 | 3 | 3.38
| 7 | 591 | Changeover time reduction (Line 4) | 3 | 3 | 0 | 1 | 9 | 3 | 1 | 3 | 0 | 2.86
| 8 | 474 | Paper and cartridge usage reduction | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 9 | 0.97
| 9 | 493 | Waste reduction (Line 6) | 3 | 9 | 3 | 3 | 9 | 3 | 1 | 9 | 3 | 5.32
10
11
12
13
14
15
www.chools.in
Guidelines:
The Project Prioritization Matrix (PPM) is a numerical scoring method that is used to determine the relative value of different projects.
It is subjective to a degree and the weights and scores are matters of personal judgment.
The score of each project equals to the project’s score for each criterion times the weight.
You need only to fill the white cells.
How to Set the Scores:
1. Sponsorship
[9] Director-level sponsor identified, duties specified, and sufficient time committed and scheduled
[3] …
[1] …
[0] Sponsor not identified or has not accepted any item in the charter
2. Benefits to stakeholder
Customer - (e.g. customer satisfaction)
[9] Substantial and statistically significant increase in overall customer satisfaction (or loyalty)
[3] …
[1] …
[0] Unclear or non-existent customer satisfaction impact
Shareholder - (e.g. financial benefits)
[9] Hard net savings greater than $250,000 or Excellent ROI
[3] …
[1] …
[0] Unclear or non-existent revenue impact or ROI
Employee - (e.g. employee satisfaction)
[9] Substantial and statistically significant increase in overall employee satisfaction (or loyalty)
[3] …
[1] …
[0] Unclear or non-existent employee satisfaction impact
3. Team members
[9] Correct team members recruited for the project and time commitments scheduled
[3] …
[1] …
[0] Team members not recruited or not available
4. Resources availability
[9] Needed resources available when needed
[3] …
[1] …
[0] Resources not available, or restrictions on access to resources
5. Learning opportunity
[9] The project will provide a high opportunity to gain valuable knowledge and skills for team members and for the company as a whole
[3] …
[1] …
[0] Learning opportunity is very low
6. Time to complete
[9] The project will be completed in less than 3 months
[3] …
[1] …
[0] The project will take more than 12 months to be completed
7. Deliverable
[9] New or improved process, product or service to be created as a result of the project
[3] …
[1] …
[0] Deliverable is poorly or not speciﬁcally defined
8. Methodology or technique
[9] Using of project methodology or technique such as DMAIC or Kaizen
[3] …
[1] …
[0] Usefulness of project methodology or technique not apparent
9. Image of company
[9] Image of company will significantly improve
[3] …
[1] …
[0] Image of company will not be affected

## Method 2 - PPI
Improvement Projects - Selection - Pareto Priority Index
|  |  | Between 0 and 1 | In years | Implementation & ongoing | Savings |  | Index value
| # | Project Title | Probability of Success | Time to Completion | Costs | Benefits | ROI % (optional) | PPI Score
1 | 445 | Spoilage reduction (Line 4) | 0.55 | 0.6 | 14000 | 320000 |  | 20.9524
2 | 461 | Stretch film wrapping usage reduction | 0.75 | 0.5 | 1100 | 11900 |  | 16.2273
3 | 414 | Energy consumption reduction | 0.5 | 1 | 4200 | 32775 |  | 3.9018
4 | 557 | Packaging material usage reduction | 0.66 | 1.2 | 29300 | 205000 |  | 3.8481
5 | 213 | Coolant usage reduction | 0.4 | 1.5 | 11900 | 112200 |  | 2.5143
6 | 432 | 5S implementation in workshop area | 0.8 | 0.5 | 14000 | 52000 |  | 5.9429
7 | 591 | Changeover time reduction (Line 4) | 0.9 | 1 | 17500 | 274000 |  | 14.0914
8 | 474 | Paper and cartridge usage reduction | 0.8 | 0.75 | 4500 | 20000 |  | 4.7407
9 | 493 | Waste reduction (Line 6) | 0.63 | 0.8 | 7900 | 144000 |  | 14.3544
10
11
12
13
14
15
www.chools.in
Guidelines:
The Pareto Priority Index (PPI) is a simple way for prioritize improvement projects. It allows to compare among various projects in order to select the most promising and profitable.
The PPI is calculated as: PPI = (Savings * Probability of success) / (Cost * Time to completion).
When two or more projects have similar PPIs, a judgment must be made on other criteria.
You need only to fill the white cells.
Definitions:
Savings – The dollar amount that reflects savings that will result from implementing the project. This should be determined by the accounting department.
Costs – The dollar amount of implementing the project. This should be determined by the accounting department.
Probability of success - How likely the project is to achieve its goal.
Completion time – The time required for the project team to achieve the project goal.