## Sheet1
PROBLEM IDENTIFICATION, SELECTION AND SOLVING PROCESS
DMAIC | PROCESS STEPS | PURPOSE AND OUTCOME |  |  | GLOBAL 8D
SIX SIGMA |  |  |  |  | D0
Single Agenda for Quality updated every quarter.
Efficency related problems comes from individual
departements
Consensus based Prioritization
1. Consult Latest Engineering Drawings and Design
Specifications when necessary
2. Develop detailed process map
|  | 2.1 | List all the processes involved
|  | 2.2 | List of process sequences
|  | 2.3 | List of all input and output of processes
|  | 2.4 | Confirm measurment capability of each
process
3. Develop Part List
|  | 3.1 | All parts involved in each process
|  | 3.2 | Gather supplier's information for each part
involved
- Supplier's capability
- Supplier's Measuring/ Gauging system
Identify DESIGN, PROCESS and PARTS QUALITY
factors critical to concerns
D1
Each PROCESS/ PARTS QUALITY Critical-X project is
assigned to appropriate, Black Belts, Green Belts
VRTs etc.
|  | 1. Problem Statement |  |  | D2
Object & Defect: Wgat's wrong with what ?
2. Problem Descriptiion and Fact- Finding. Is.Is Not Analysis, etc.
- What ?
- When ?
- Where ?
- Howe Big ?
D3
When necessary, develop Interim Containment Action ( ICA )
- ICA Verfification
- ICA Validation
D4
Gather facts and measureable data
Develop Is/ Is Not and Root Cause Theories
D5 & D6
Find Root Causes for the Critical - X - project
- Root Cause verification
Identify escape points in process'
Develop Permanent Corrective Action ( PCA )
Verification of PCA
Validation of PCA
Develop and Execute Implementation plan for PCA
D7
Prevent recurrence of this concern as well as similar
concerns
D8
Project Closing Criterial
- What are requirements for closing a project ?
File Global 8D documentation in G8D Database
www.chools.in
SAQ / TGW
In - Plant Emerging Concern
Cost Reduction Opportunities
Customer Satisfaction / Process Improvement
VRT Champions, LVT Champion , Quality Leader , Master Black Belts ,Finance , Purchase . FCSD , Sales & Marketing , MP& L, HR
Pick Important Concerns
Process Study
Develop List of Critical X ( Smaller Ys )
Assign Each critical Ys Project
Black Belt
Green Belt
VRT
NWG
Develop Problem Statement & Problem Description
Develop, Verify and Implement ICA if necessary
Identify Measurable & confirm Measurement process and Capabilities
Analyze
Improve
Control
External Expertise as Needed
Y = Xdesign + Xprocess + Xparts- Quality + X …..
Close Project and Archive Documents
D E F I N E
M E A S U R E
ANALYZE
IMPROVE
CONTROL
Product Quality
Efficiency Improvement