## Guidelines
Communication Plan Guidelines
Effective Communications Must have the following characteristics:
A consistent formal process; Simple and understood by all; Contain current information; Have a feedback loop built into the process
Will help: Build and maintain trust; Prevent rumors; Enlist and enroll the participation of employees in the pursuit of achieving objectives
What’s the best way to communicate with your team, key stakeholders and project champion?
-Who is your audience?
-What is the tool or media you will use to communicate?
-What is the purpose of your communication?
-What are you key messages?
-Who is the owner of the communications task?
-What is the timing and frequency of the communications?
Identify the various audiences you will need to communicate to:
Executive Team; Departmental Managers; Administration; Risk Management; Sales; Marketing; HR; IT; Consumer Relations; Engineering; Finance; Legal; Customers; Salaried; Hourly; Marketplace; South America; North America; Europe; Asia; Distributors
Identify the media by which you will communicate to the groups above:
Voice Mail; E-Mail; Posters; Memos; Oral Communication; Formal Presentations; “Elevator Speech”
For each Stakeholder identified, determine:
-Are they critical for development of project tasks (Project Enabling Stakeholders) or critical for the successful implementation of a solution (Project Implementation Stakeholders)?
-What concerns can you anticipate for each Stakeholder?
-What positive outcomes exist for each Stakeholder?
-What will be your message for each Stakeholder?
-A Stakeholder Analysis should be completed/revised as critical aspects of the project change (I.e. scope changes, solution options become more visible, etc.)
-A Stakeholder Analysis should be a confidential document
Communication Plan
Comes in many forms, but Key Elements include:
Target of communication; Frequency of communication; Media to be used, Be specific,
Example 1: A 30 minute verbal conversation, every Friday at 4 p.m., including topics …
Example 2: A weekly written update, to be completed by Friday end-of-day, to include, a) Activities completed this past week, b) activities to be completed next week, c) currents risk to on-time, on-budget completion, & d) action plan to resolve risks.
Revise, as necessary, as project matures; Especially important to revise/update for project implementation
Obtain verbal agreement on each plan element from target of communication
http://chools.in/

## Communciation Plan
Communication Plan
Topics of Discussion / Key Messages | Purpose | Audience | Owner | Media | Frequency | Timing | Notes / Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
http://chools.in/