## Control
Document | MRD.MCI.TMP.004 - Project Charter Template
Version | v1.02
Date | 2008-11-10
Author | Scott Odegaard
Source | https://sww-knowledge.shell.com/knowhow/livelink.exe?func=ll&objId=96412297&objAction=properties
Public | https://sww-knowledge.shell.com/knowhow/livelink.exe?func=ll&objId=83276626&objAction=properties
History
Date | Version | Author | Comments
2008-11-10 | 1.02 | Scott Odegaard | First official version
2008-11-14 | 1.03 | Radney Cray | Removed Wing-ding font

## Charter
Project Charter: |  | Customer Master Batch Create / Update |  |  |  | Project Number: <######>
Business Case (Purpose) |  |  |  | Opportunity Statement (Pain)
The Project team wants to improve the Customer Mass upload Processes. Based on the Year-2008 data, the mass Load Process average turnaround time was 15 Business days against the target of 3-5 business days. The project team fucusses on Customer create & update process. By improving the Customer create & update mass load process, the TAT can be achievable. The approximate monthly volume was - 122,500 updates/creates with mass load being 103,000 and BSP - 19,500, Process involves 5 repetitve loading / validation interaction steps between FOD and ATS -Big pain area to the business, Monthly refresh / Year End Freeze increases the TAT by a minimum of 5 business days. Improving the process with result in a Substantial savings of $300k to the Sales Support team in Houston. Note:In 2008 Technical Asset FO Data Megellan, ran 400 mass loads updates with an average TAT of 4 business days. We can replicate the same in the across FO-Data. |  |  |  | * Based oin the data for Year-08, the average TAT for customer mass load process is - 15 business days * Anticipated increase of mass load requests from US Lubes as a result of mass change transaction (XD99) not available in GSAP. * US Lubes Sales Support 2 approximate customer create is 20 BSP per day * US Lubes MRD approximate customer create approval is 50 BSP per day. * 400 customer create ship-tos would take 20 business days to complete E2E* In addition to GSAP go-live activities Customer FO Data has a necessity for mass updates in order to support run and maintain business needs, ie, sales reorganisation, on going monthly / quarterly credit evaluation, etc. * 2008 162 Customer FO Data mass loads completed with 65 completing beyond 14 bsiness days * FO Data KPI failed last 2 of 3 months as a result of missed TAT Turn Around Time (TAT) in other FO Data areas - 2008.Total FO Data mass load completed were 677 and 167 were completed beyond 14 business days. * As part of the normal day to day funtions, US Lubes frequently have customer requests to create high ship-to volume customers, with a quick set up turnaround requirement. *Post go-live US Lubes have 14,000 pending ship-to accounts waiting for set up. *These are national accounts with high revenue. * In addition to the pending national accounts, US Lubes averages one request per month, with this type of criteria of high volume of 400 or more ship-to accounts with quick set up turnaround. *Global KPI for customer set up is 6 business day end to end
Scope |  |  |  | Goal Statement (Targeted Gain)
In |  |  | Out | 1. Bring Customer mass update average TAT to 5 Business days by October 31, 2009 2. 20 % increase mass load usage and decrease in manual BSP usage by October 31, 2009. 3. Bring Customer mass creation average TAT to 5 Business days by October 31, 2009. 4.2. Data quality remain at 99%.
- GSAP - Customer FO Data - Create / Update / Delete |  |  | - Legacy - Other FO Data areas - CMIR - Material Listing and Exclusion - Pricing - Output Condition Records - Ship to contacts (CRM) - EDI Table Maintenance - Material Determination
Benefit Statement
1.There will be $300k .Approx- L1-Non-FO benefits from this project. 2. Improve customer creation / update batch loading turnaround time. - L3 3. Need to identify potential L2 benefit during the Measure phase of the project.
Project Schedule |  |  |  | Project Team/Resources
| Start | Finish | Comment | Champion : | Tom Kunz / Scott Odegaard
Define |  |  |  | Owner : | Dave Hammer
Measure |  |  |  | Green Belt | Mary Brimhall
Analyse |  |  |  | MBB/Coach | Sathish Narayanan
Improve |  |  |  | Team Members | Pat Patterson - FPS-US Lubes, STBC Design - Melissa kaam
Control |  |  |  |  | Paul ling -ATS Manager, Rick Papso - Sale/Support Manager
Mary Arispe-Herrera - US Lubes CMD Team lead, Manila team member-Name's to be furnished end of Define phase
Deployment office use: |  |  | 0 |  | Project Number:
Proposed Methodology |  |  | DMAIC | Project Charter Checklist
Project Priority |  |  | High
Location of Project |  |  |  | Optional checklist to help focus the charter |  | 0/1/2
Originator in the line |  |  |  | Business Case |  | 0
RBI support person |  |  |  | Expected impact on / benefit to business is clear (tie to Business Priorities?) |  | 0
|  |  |  | Link to Customer is clear & strong? |  | 0
Earliest start of project |  |  |  | It's clear what level of financial benefits are expected? |  | 0
Latest start of project
Comment: |  |  |  | Opportunity Statement |  | 0
|  |  |  | Project Charter is clearly focused on the need for (breakthrough) improvement? |  | 0
|  |  |  | Opportunity Statement is focused on a specific business process / activity? |  | 0
|  |  |  | Opportunity is explicitly defined in the opportunity statement of the Charter? |  | 0
Co-operation/approval requirement from other departments (Which?)
|  |  |  | Goal Statement |  | 0
|  |  |  | Has a clear primary metric been identified? |  | 0
|  |  |  | Has a clear secondary metric been defined to avoid sub-optimization? |  | 0
Metrics defined are S.M.A.R.T.?
Benchmark levels and targets for primary metric have been established?
Other Comments |  |  |  | Scope |  | 0
|  |  |  | Is the start & end point of your process, to be improved, known? |  | 0
|  |  |  | Any exclusions / off limits are specified within Charter? |  | 0
Any expenditure or other resource constraints specified?
|  |  |  | Team |  | 0
|  |  |  | A Project Sponsor is named & accountable for project success? |  | 0
|  |  |  | Have the team members been defined ? |  | 0
Business Plan Priorities |  |  | High/Medium/Low impact | Have critical skills / needs been identified / contacted? |  | 0
Safety |  |  | N/A | Have team members got sufficient time available to participate? |  | 0
Reserves Replacement |  |  | N/A
Production (2005 - 2006) |  |  | N/A | Project Plan |  | 0
Growing the Resource Base |  |  | N/A | Project can reasonably be expected to be completed in 4-6 months? |  | 0
Effective Project Delivery |  |  | N/A | Are the milestones identified & agreed with the Sponsor?
Operational Excellence |  |  | N/A | Has a clear end date been defined and agreed with the Sponsor?
Competitive Cost Structure |  |  | N/A
|  |  |  | Overall |  | 0
Note on B4: The business case should address these questions: - Does this project align with other business initiatives? - What benefits will be derived from this project? - Benefits specific to this project? - Has the value of the benefits been quantified? - What is the focus for the project team? - What impacts will this project have on other business units and employees?
Note on E24: Full-DMAIC, DMEDI, Lean Design, DMAIC, etc.
Note on E25: High/Medium/Low
Note on E26: Assen/ Stavanger/ Den Haag/ Aberdeen/ Kristiansund/etc.
Note on E28: This is the person who will receive the feedback on what is going to happen with the charter
Note on E29: Could be a (Master) Black Belt, Account Manager or other person who has helped develop the charter
Note on E31: Put in a date if the project should not start before a certain date, e.g. depending on other projects, resources available from the line, etc.
Note on E32: Put in a date if the project should not start before a certain date, e.g. depending on other projects, resources available from the line, etc.
Note on G4: The opportunity statement should address these questions: - What is the impact “pain” on our customers? - What is the impact “pain” on our business? - What is the impact “pain” on our employees? - How extensive is the problem? - What is wrong or not working? - When and where do the problems occur? - Does it make strategic sense to address this problem?
Note on G41: Specific Measurable Achievable Relevant Time bound
Note on H14: Typically a senior leader, main task to ensure resources are available and other departments are aligned with the project objectives
Note on H15: "The Person owning the problem and who will own the solution" - The Project Owner is the person who will be responsible for implementing the project
Note on I7: The goal statement should address these questions: - What does the team expect to accomplish and how will it be measured? - What is the primary metric that needs to be improved? - What is the secondary metric that (we need to keep an eye on and must not get worse)
Note on I10: What will be the tangible "hard" deliverables / results? What will be the intangible, "soft" deliverables / results? What is the timetable for benefits delivery?
Note on I26: Answer to the question: 0: No 1: To a certain extent 2: Yes

## Charter Guidance
Opportunity Charter: |  |  | Project Title
Business Case (Purpose) |  |  |  | Opportunity Statement (Pain)
The business case should address these questions: - Does this project align with other business initiatives? - What benefits will be derived from this project? - Benefits specific to this project? - Has the value of the benefits been quantified? - What is the focus for the project team? - What impacts will this project have on other business units and employees? |  |  |  | The opportunity statement should address these questions: - What is the impact “pain” on our customers? - What is the impact “pain” on our business? - What is the impact “pain” on our employees? - How extensive is the problem? - What is wrong or not working? - When and where do the problems occur? - Does it make strategic sense to address this problem?
Scope |  |  |  | Goal Statement (Targeted Gain)
In |  |  | Out | The goal statement should address these questions: - What does the team expect to accomplish and how will it be measured? - What is the primary metric that needs to be improved? - What is the secondary metric that needs to be improved? - What will be the tangible, “hard” deliverables/results? What will be the intangible, “soft” deliverables/results? - What will be the timetable for delivery of results? - Will it meet Cost and production selection criteria for projects which only cover either Opex, Capex or Production ?: - Opex: USD 500.000 per annum 100% - Yes/No - Capex: USD 500.000 per annum 100% - Yes/No - Production: 100 BOE/d 100% - Yes/No N.B. Meeting selection criteria needs to be agreed with FPL
Benefit Statement
The project scope should address these questions: - What areas of the business are included? - What areas of the business are not included? - What, if anything, is outside the project boundaries? - What constraints must the team work under?
Project Schedule |  |  |  | Project Team/Resources
| Start | Finish | Comment | Champion
Define |  |  |  | Owner
Measure |  |  |  | Project Lead/BB
Analyse |  |  |  | Team Members
Improve
Control
Deployment office use: |  |  | Project Title |  | Project Number:
Check list |  |  | Project Title
Proposed Methodology |  |  |  | Project Charter Checklist
Project Priority
Location of Project |  |  |  | Optional checklist to help focus the charter |  | 0/1/2
Originator in the line |  |  |  | Business Case |  | 0
RBI support person |  |  |  | Expected impact on / benefit to business is clear (tie to Business Priorities?) |  | 0
Link to Customer is clear & strong?
Earliest start of project |  |  |  | It's clear what level of financial benefits are expected?
Latest start of project
Comment: |  |  |  | Opportunity Statement |  | 0
Project Charter is clearly focused on the need for (breakthrough) improvement?
Opportunity Statement is focused on a specific business process / activity?
Opportunity is explicitly defined in the opportunity statement of the Charter?
Co-operation/approval requirement from other departments (Which?)
|  |  |  | Goal Statement |  | 0
|  |  |  | Has a clear primary metric been identified? |  | 0
Has a clear secondary metric been defined to avoid sub-optimization?
Metrics defined are S.M.A.R.T.?
Benchmark levels and targets for primary metric have been established?
Other Comments |  |  |  | Scope |  | 0
Is the start & end point of your process, to be improved, known?
Any exclusions / off limits are specified within Charter?
Any expenditure or other resource constraints specified?
|  |  |  | Team |  | 0
A Project Sponsor is named & accountable for project success?
Have the team members been defined ?
Business Plan Priorities |  |  | High/Medium/Low impact | Have critical skills / needs been identified / contacted?
Safety |  |  |  | Have team members got sufficient time available to participate?
Reserves Replacement
Production (2005 - 2006) |  |  |  | Project Plan |  | 0
Growing the Resource Base |  |  |  | Project can reasonably be expected to be completed in 4-6 months?
Effective Project Delivery |  |  |  | Are the milestones identified & agreed with the Sponsor?
Operational Excellence |  |  |  | Has a clear end date been defined and agreed with the Sponsor?
Competitive Cost Structure
|  |  |  | Overall |  | 0
Note on E6: jan.duinhoven: Safety Reserve Replacement Ratio
Note on E28: Full-DMAIC, DMEDI, Lean Design, DMAIC, etc.
Note on E29: High/Medium/Low
Note on E30: Assen/ Stavanger/ Den Haag/ Aberdeen/ Kristiansund/etc.
Note on E32: This is the person who will receive the feedback on what is going to happen with the charter
Note on E33: Could be a (Master) Black Belt, Account Manager or other person who has helped develop the charter
Note on E35: Put in a date if the project should not start before a certain date, e.g. depending on other projects, resources available from the line, etc.
Note on E36: Put in a date if the project needs to have finished before a certain date, .e.g to meet an external milestone, promise, to tie-in with another project, etc.
Note on G45: Specific Measurable Achievable Relevant Time bound
Note on H15: Typically a senior leader, main task to ensure resources are available and other departments are aligned with the project objectives
Note on H16: "The Person owning the problem and who will own the solution" - The Project Owner is the person who will be responsible for implementing the project
Note on I11: What will be the tangible "hard" deliverables / results? What will be the intangible, "soft" deliverables / results? What is the timetable for benefits delivery?
Note on I30: Answer to the question: 0: No 1: To a certain extent 2: Yes

## ToR mapping
Charter | Terms of Reference | Guidance | Checklist
Business Case (Purpose) | Objective | The business case should address these questions: - Does this project align with other business initiatives? - What benefits will be derived from this project? - Benefits specific to this project? - Has the value of the benefits been quantified? - What is the focus for the project team? - What impacts will this project have on other business units and employees? | Expected impact on / benefit to business is clear (tie to Business Priorities?)
| Key Requirements |  | Link to Customer is clear & strong?
It's clear what level of financial benefits are expected?
Opportunity Statement (Pain) | Background | The opportunity statement should address these questions: - What is the impact “pain” on our customers? - What is the impact “pain” on our business? - What is the impact “pain” on our employees? - How extensive is the problem? - What is wrong or not working? - When and where do the problems occur? - Does it make strategic sense to address this problem? | Project Charter is clearly focused on the need for (breakthrough) improvement?
Opportunity Statement is focused on a specific business process / activity?
Opportunity is explicitly defined in the opportunity statement of the Charter?
Scope |  | The project scope should address these questions: - What areas of the business are included? - What areas of the business are not included? - What, if anything, is outside the project boundaries? - What constraints must the team work under? | Is the start & end point of your process, to be improved, known?
In | Scope |  | Any exclusions / off limits are specified within Charter?
Out | Not in Scope |  | Any expenditure or other resource constraints specified?
Goal Statement (Targeted Gain) | Deliverables | The goal statement should address these questions: - What does the team expect to accomplish and how will it be measured? - What is the primary metric that needs to be improved? - What is the secondary metric that needs to be improved? - What will be the tangible, “hard” deliverables/results? What will be the intangible, “soft” deliverables/results? - What will be the timetable for delivery of results? - Will it meet Cost and production selection criteria for projects which only cover either Opex, Capex or Production ?: - Opex: USD 500.000 per annum 100% - Yes/No - Capex: USD 500.000 per annum 100% - Yes/No - Production: 100 BOE/d 100% - Yes/No N.B. Meeting selection criteria needs to be agreed with FPL | Has a clear primary metric been identified?
| Criteria for Success |  | Has a clear secondary metric been defined to avoid sub-optimization?
Benefit Statement | Benefits |  | Metrics defined are S.M.A.R.T.?
Benchmark levels and targets for primary metric have been established?
Project Schedule | Project Plans |  | Project can reasonably be expected to be completed in 4-6 months?
Start |  |  | Are the milestones identified & agreed with the Sponsor?
Finish |  |  | Has a clear end date been defined and agreed with the Sponsor?
Comment | Project Completion Criteria
| Risks | Describe risks in Comments. Use risk factors from Improvement Log: Project Size, Change, Complexity, Technology
Six-Sigma | Transition SG
Define | Initiate
Measure | Discovery
Analyse | Design
Improve | Implement
Control | Parallel
Checkpoint
Project Team/Resources | Project Governance |  | A Project Sponsor is named & accountable for project success?
| Initial cost estimates |  | Have the team members been defined ?
Have critical skills / needs been identified / contacted?
Have team members got sufficient time available to participate?