## Instructions
RACI
RACI is a tool that can be used to ID Roles and Responsibilities during a change process. Click the 'LSS RACI' tab below to access the spreadsheet.
The benefit is it clearly defines task level role/Responsibility, builds accountability and ownership, useful in communications
R = Responsible – The person who performs the action/task.
A = Accountable – The person who is held accountable that the action/task is completed.
C = Consulted – The person(s) who is consulted before performing the action/task.
I = Informed – The person(s) who is informed after performing the action/task.
Accountable:
-The individual who has ultimate accountability and authority.
-There is only one accountable (A) to each task/activity.
-Accountability is assigned at the lowest level and implied at higher levels
-Accountability can not be delegated
Responsible:
-Individual/s who perform a task/activity; the doer, responsible for action/implementation.
-The degree of responsibility is defined by the Accountable person.
-Responsibility can be shared.
-While Accountability can NOT be delegated, Responsibility can be delegated.
Consulted:
-The individuals to be consulted prior to a final decision or action is taken.
-Two-way communication.
Informed:
-The individuals that need to be informed after a decision or action is taken
Process
1. Identify all of the processes/steps involved and list in the chart
2. ID who has the R,A,C, & I for each process
3. Every process/step should preferably have only one A, while all other roles can use multiple names or groups.
4. Resolve any overlaps . If there are multiple A's. In the case of multiple A's, there may be a need to "zoom in" and further detail the sub processes associated to separate the individual accounability.
5. Resolve Gaps. Try to ensure that there is an A or R assigned to each task.
www.chools.in

## LSS RACI
Project RACI Chart
R = Responsible – The person who performs the action/task.
A = Accountable – The person who is held accountable that the action/task is completed.
C = Consulted – The person(s) who is consulted before performing the action/task.
I = Informed – The person(s) who is informed after performing the action/task.
Step | Action/Task | Responsible | Accountable | Consulted | Informed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
www.chools.in