## Action plan
SOLUTION IMPLEMENTATION PLAN
S. No. | Solution | Solution Description | Actions | Responsibility | Start Date | End date | %Complete | Status | Remarks
1 | In GCoA for each GL account a user guide be written to help country controller SME to understand what the GL account is to be used for | Definitions of all the accounts are already existing. Need to educate the implementation team on how to find these definitions |  |  | 2008-08-05 | 2008-09-30
1.1 |  |  | Document the process with necessary screen shots of finding the information | TIM |  |  | 100% | Amber | COMPLETED as a part of Solution no. 10 | 10% | Red
1.2 |  |  | Ensure the KT materail of the Implementation team is updated | SUMAN/NANCY |  |  | 90% | Amber | COMPLETED - Training material ready and shared with Nancy. Awaiting confirmation on inclusion and delivery as a part of KT material. | 20% | Amber
2 | Document Streamline approval criteria and contacts | Develop a detailed list of all the streamline contacts for different categories of accounts. Approval process/criteria needs to be documented | [7 empty] | 30% | Green
2.1 |  |  | Develop list of streamline contacts for different categories of account requests | TIM |  |  | 100% | Green | COMPLETED | 40%
2.2 |  |  | Develop a document which describes the process of getting the approval from the streamline contacts and clearly mentions the criteria on which the approvals are done | TIM |  |  | 100% | Green |  | 50%
3 | Document High level requirement of Central FSS and GSAP and provide that to FN implementation team | To communicate in clear terms the expectation of the Central FSS when requests are submitted | [7 empty] | 70%
3.1 |  |  | Develop FAQs for the queries that are asked which gets raised at the time of submitting the request | MO |  |  | 100% | Green | COMPLETED | 80%
3.2 |  |  | Update the application with the Instructions Tab containing the above information in the form of Check lists | MO |  |  | 100% | Green | COMPLETED | 90%
3.3 |  |  | Share the information with implementation team and get their buy in | MO |  |  | 100% | Green | COMPLETE -31st Oct | 100%
3.4 |  |  | Ensure the information is included in the KT material of the implementaiton team | SUMAN/NANCY |  |  | 90% | Amber | COMPLETED - Training material ready and shared with Nancy. Awaiting confirmation on inclusion and delivery as a part of KT material.
4 | Dedicated resource for processing new GL account requests in MRD | Provide dedicated resource in MRD to process the new GL account creation request |  |  | 2008-08-05 | 2008-09-30
4.1 |  |  | Confirm resourcing plan | GADIYAR |  |  | 100% | Green | COMPLETED
4.2 |  |  | Confirm interim plan to manage production before the resource is productive | GADIYAR |  |  | 100% | Green | COMPLETED
4.3 |  |  | Confirm resource training plan | GADIYAR | A DEDICATED RESOURCE WILL BE MANAGED BY MRD BASED ON VOLUMES |  |  |  | PRINCIPAL ADHERENCE TO THE RECOMMENDED INTENT - AGREED BY MRD
4.4 |  |  | Resource on board | GADIYAR
4.5 |  |  | Resource training | GADIYAR
4.6 |  |  | Resource productive | GADIYAR
5 | Requestors not to submit request in bulk. Stagger the inflow to match the capacity | Educate implementation team members about the limitation of capacity of the team processing the New GL account creations requests |  |  | 2008-08-05 | 2008-09-30
5.1 |  |  | Establish process capacity | SUMAN |  |  | 100% | Green | COMPLETED
5.2 |  |  | Ensure process capacity information are inlcuded in the training material of the Implementation team | SUMAN |  |  | 100% | Green | COMPLETED - Process control plan has this information . Link will be provided in the KT material
6 | During the pre go-live the FN implementation team focal point(one person) can submit requests for the country | This is to ensure that there is only one requestor from any country at any point of time
6.1 |  |  | Develop a list of focal points for all the countries | NANCY |  |  | 90% | Amber | Awaiting respose from Nancy
7 | After Post go-live all the new GL account request to be reviewed and approved by Country controllers(or SME). Each country to have only one requestor from controllers team with a back up | This is to ensure that there is only one requesotor from any country at any point of time
7.1 |  |  | Get approval from Streamline | TIM |  |  | 100% | Green | Major action against this solution was to initiate the role creation request. This has been done by creating a role FSS 275
7.2 |  |  | Submit role design change request | TIM |  |  | 100% | Green
7.3 |  |  | Confirm retrofit plan | TIM |  |  |  | Amber
7.4 |  |  | Confirm Training and other requirements | TIM |  |  |  | Amber
7.5 |  |  | Develop Implementation plan | TIM/SUMAN |  |  |  | Amber
7.6 |  |  | Confirm implementation | TIM |  |  |  | Amber
7.7 |  |  | Confirm list of contacts for each country | TIM |  |  |  | Amber
8 | Avoid waiting of applications – before and after processing in Central FSS, MRD and at DA | To reduce the WIP by ensuring that requests are actioned as soon as possible and transferred to the next process step immediately after the work is over at the previous process step
8.1 |  |  | Establish Process capacity | SUMAN |  |  | 100% | Green | COMPLETED
8.2 |  |  | Establish the benefit of following the single piece flow system | SUMAN |  |  | 100% | Green
8.3 |  |  | Implement first phase of Single piece flow system before the resources are on board | TEAM |  |  | 100% | Green
8.4 |  |  | Full implementation of single piece flow system once the resources are on board | TEAM |  |  | 100% | Green
9 | Train FN implementation team on hierarchy design of when a GL account is used, a WBS element is used etc. | To ensure that the requestors from the implementaiton team are aware of the hierarchy design
9.1 |  |  | Gather information from Shell learning | MO |  |  | 100% | Green | Document found within GSAP and will be shared with Implementation team after necessary correction
9.2 |  |  | Develop training material in the form of slide set | MO |  |  | 100% | Green
9.3 |  |  | Get buy in from Implementation team | SUMAN |  |  | 100% | Green
9.4 |  |  | Confirm training slides included in the KT material of the Implementation team | SUMAN |  |  | 90% | Amber
10 | Educate implementation team and country controllers about the streamline design objective | To ensure that the requestors are aware of the streamline design objective and appreciate the same
10.1 |  |  | Study and update the Streamline Design strategy document | TIM |  |  | 100% | Green | COMPLETED - Training material ready and shared with Nancy. Awaiting confirmation on inclusion and delivery as a part of KT material.
10.2 |  |  | Summarise the streamline Finance Design strategy | TIM |  |  | 100% | Green
10.3 |  |  | Develop training material in the form of slide set | TIM |  |  | 100% | Green
10.4 |  |  | Get buy in from Implementation team | TIM |  |  | 100% | Green
10.5 |  |  | Confirm training slides included in the KT material of the Implementation team | SUMAN |  |  | 90% | Amber
11 | Train back up resource in Central FSS to support Mo | To ensure uninterupted availability of resource to work on new GL account request | [5 empty] | Green
11.1 |  |  | Establish resource requirement | MO |  |  | 100% | Green | COMPLETED
11.2 |  |  | Resource on board | MO |  |  | 100% | Green
11.3 |  |  | Resouce productive | MO |  |  | 100% | Green
12 | Measure, track and report KPI for New GL account request rejection rate and end to end TAT | To establish proper control on the process end to end with clear understanding of the deliverable at each stage of the process
12.1 |  |  | Establish KPI requirement | SUMAN |  |  | 100% | Green | COMPLETED
12.2 |  |  | Establish the audience for KPI reporting | SUMAN |  |  | 100% | Green
12.3 |  |  | Formalise KPI reporting | SUMAN |  |  | 100% | Green
www.chools.in